## 16-03-2026
S.no | Parameter | Weightage | Unit of Measure | Jawalgera | Ambada | Sagapara | Bhopalgarh | Tharad | Honnati(50 MW) | Aland(W)(212 MW) | Aland (S)(120MW) | Aland(B) | Pathmada (S)(45MW) | Byagwat | Chittaguppa | Halburga | Farahtabad | NEPL | MH-50
1 | Site Field quality plan | 10% | Percentage completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Approved BOQ status | 10% | % completion | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | NC closure status | 25% | % NC closed | 99.27% | 54.11% | 100% | 98.4% | 95.25% | 92.69% | 64.3% | 90.17% | 94.67% | 100% | 90% | 53.85% | 60% | 80% | 13.33% | 94.67%
4 | Request for inspection compliance status | 20% | % complied | 99.22% | 0% | 100% | 99.57% | 88.31% | 100% | 84.16% | 74.97% | 42.59% | 72.95% | 13.64% | 26.98% | 20.31% | 15.25% | 0% | 21.8%
5 | No of observation raised | 2.5% | Number 0.5 Marks deducted for every observation raised | -71% | -31% | -21% | -38% | -106.5% | -16% | -139.5% | -94.5% | -7.5% | -16.5% | -2.5% | -7% | -3% | -4% | -4% | -7.5%
6 | No of observation closed on time | 2.5% | Number 0.5 marks given for every observation closed | 70% | 7.68% | 21% | 37% | 103% | 15% | 122% | 87% | 7% | 16.5% | 2% | 5.5% | 1.5% | 3% | 0% | 7%
7 | Resource deployed by contractor | 10% | 1 per 20 MW | 100% | 0% | 100% | 100% | 100% | 100% | 54.55% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
8 | Stop Work due to quality issues(QUATERLY) | 5% | 100% score for 0 events 80% score for 1 event 60% score for 2 events 40% score for 3 events 0% score if more than 3 events | 100% | 100% | 100% | 100% | 100% | 80% | 100% | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Hours of quality training | 5% | Number of hours trained per 1000 hour worked | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
10 | Incoming material inspection compliance rate | 10% | % complied (QA Reports submitted / QA inspection required - GRN) | 100% | 100% | 100% | 100% | 100% | 100% | 98.46% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 80%
|  |  | Total Rating | 84.64% | 42.95% | 85% | 84.49% | 86.39% | 88.15% | 72.77% | 82.35% | 77.17% | 84.59% | 45.22% | 38.82% | 39.03% | 43.03% | 33.23% | 56.01%
| Parameter | Weightage | Unit of Measure | Jawalgera(50MW) | Ambada+Mahadev(198MW)& PP | Sagapara(40MW) | Bhopalgarh(150MW) | Tharad(52.5MW) | Honnati(50 MW) | Aland(W)(212 MW) | Aland (S)(120MW) | Aland (B)(41.5 MW) | Pathmada (S)(45MW) | Byagwat | Chittaguppa | Halburga | Farahtabad | NEPL | MH-50
| FOM | 20% |  | 72 | 1341 | 14 | 19 | 122 | 0 | 3 | 41 | 5 | 15 | 0 | 0 | 0 | 0 | 3 | 4
| FOM Closed |  |  | 72 | 300 | 14 | 19 | 122 | 0 | 1 | 39 | 5 | 15 | 0 | 0 | 0 | 0 | 2 | 4
| Total Observation | 80% |  | 110 | 22 | 40 | 50 | 182 | 25 | 270 | 163 | 15 | 33 | 4 | 13 | 6 | 8 | 7 | 15
| Observation Closed |  |  | 108 | 22 | 40 | 48 | 178 | 24 | 239 | 152 | 14 | 33 | 3 | 11 | 3 | 6 | 0 | 14
| NC |  |  | 32 | 2158 | 2 | 26 | 31 | 7 | 9 | 26 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0
| NC Closed |  |  | 32 | 520 | 2 | 26 | 28 | 6 | 5 | 22 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| NC closure overall |  |  | 0.99273 | 0.54113 | 1 | 0.984 | 0.9525 | 0.92686 | 0.64296 | 0.90171 | 0.94667 | 1 | 0.9 | 0.53846 | 0.6 | 0.8 | 0.13333 | 0.94667
| Req.RFI |  |  | 1080.4623 | NIL | 802 | 1775.865 | 785.5 | 1053 | 3200 | 1716 | 410.66 | 678.3833 | 124.6 | 126 | 128 | 118 | 144.4 | 192.675
| RFI Closed |  |  | 1072 | NIL | 802 | 1768.2833 | 642 | 803.25 | 1472 | 987.3357 | 69 | 151 | 17 | 34 | 26 | 18 | 0 | 42
| RFI Required till date |  |  | 886 |  | 487 | 1423 | 727 | 721 | 1749 | 1317 | 162 | 207
| RFI Score |  |  | 0.99217 | 0 | 1 | 0.99573 | 0.88308 | 1 | 0.84162 | 0.74969 | 0.42593 | 0.72947 | 0.13644 | 0.26984 | 0.20312 | 0.15254 | 0 | 0.21798
| Training personnel |  |  | 0 | 0 | 0 | 0 | 14 | 19 | 58 | 20 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 124
| Training sessions |  |  | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| TOPICS | [6 empty] | MMS Alignment, Degree, Ground clearance , Fastners should be tight as per given standards and all accessories should be used properly Before Laying IR must be checked, follow the Laying process, used jacks and roller, and work maintain as per approved drwg | "1.Module Ground Clearance – Ensure proper ground clearance of modules as per drawing/specification before final torquing. 2.Bracket Nut-Bolt Tightening – All saddle brackets nut-bolts must be tightened properly with required torque. Table to Table Alignment – Check proper alignment between tables before tightening bolts. 3.Torque Wrench Use – Always use a calibrated torque wrench to achieve correct torque value. Final Inspection – After tightening, perform visual and physical inspection to ensure no loose nut-bolts remain." "1.Surface Preparation – Roof surface should be properly cleaned. Remove dust, loose particles, oil, and standing water before starting waterproofing work. 2.Material Application – Apply waterproofing material (bitumen / coating as per specification) uniformly with proper thickness as per approved method statement. 3.Slope and Drainage – Ensure proper roof slope towards drain points so that water does not accumulate on the roof surface. 4Curing and Protection – After application, allow proper curing and protect the waterproofing layer from damage during further construction activities." "TOPIC- BRICK WORK, PLASTER,FINISHING WORK " | "1. Mandatory Flat length maintain 2. Proper Continuous Welding 3. Avoid Tack Welding 4. Chipping & Bituminuous Paint Apply 5. All Extension Flat connection to earthmat 6. Proper size rod & welding machine usuage 7. PPE'S Usuage" "1. Proper PPE usage and safety compliance guidelines. 2. URS positioning and hub radius measurement accuracy. 3. Blade assembly requirements, including crane selection and positioning. 4. Verification of TPI and load chart before commencing work. 5. Step-by-step blade assembly procedure. 6. Torque values for blade studs and rotor jig bolts. 7. Pre-lifting checks for all ropes, slings, and lifting checklists. 8. Requirement of 100-ton superlift counterweight. 9. Support crane positioning and safe lifting procedure. 10. Complete WTG installation procedure briefing. 11. Common challenges faced during installation and preventive measures. 12. WTG cleaning requirements and best practices. " "1. Incoming material documentation procedures. 2. Offloading protocols. 3. Offloading area clearance requirements. 4. Lifting tools and tackles – condition check and handling protocol. 5. Loading and offloading clearance process. 6. Guide rope usage guidelines. 7. Positioning procedures for 400T and 160T crawler cranes during loading and offloading. 8. Common challenges faced during loading and offloading operations. 9. Proper PPE usage and safety compliance guidelines" "1. Conductor frayness check 2. Insulator check 3. Tension hardware proper crimping 4. Double tension & Cotter pin usuage 5. Jumper sag & clearance maintain 6. Tower tightness & correct size hardwares 7. PPE's usuage" | "1. Cement mortar Mix Ratio and brick wall thickness checking 2. cement mortar thickness shall be as per Dwg 3.slab De-shuttering process 4. Required tools and tackle 5. Safety requirements 6. Hacking the Rcc structures before starting plastering work" "1. HT cable laying 2. Sand laying and checking 3. Bricks laying in HT trench 4 Safety requirements" | "1. Column height checking 2. Column plumb cheking 3. Properly covered block provided 4. Properly sterriups bending." "1. Marking 2. Bar binding 3. Shuttering 4. Casting" | Concrete & curing after casting sessions, structure proper curing (MCR)
| Resource deployed by contractor |  |  | 1 | 0 | 2 | 2 | 2 | 2 | 6 | 6 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0
| Resource required at site |  | 1 per 20 MW | 1 | 9 | 2 | 2 | 2 | 2 | 11 | 6 | 2 | 2 | 0 | 0 | 1 | 0
| Resource score |  |  | 1 | 0 | 1 | 1 | 1 | 1 | 0.54545 | 1 | 1 | 1 | 0 | 0 | 1 | 0
| IMIR submitted |  |  | 133 | 100 | 69 | 100 | 182 | 230 | 128 | 395 | 3 | 18 | 0 | 0 | 0 | 0 | 4 | 4
| IMIR required |  |  | 133 |  | 69 | 100 | 182 | 230 | 130 | 395 | 3 | 18 | 0 | 0 | 0 | 0 | 4 | 5
| IMIR closure |  |  | 1 |  | 1 | 1 | 1 | 1 | 0.98462 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0.8
| Work Stop (Active work stop events) |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Training Till date |  |  | 128 | 80 | 47 | 123 | 142 | 108 | 119 | 93 | 9 | 32 | 3 | 18 | 8 | 5 | 2 | 4 | 917
| Total Participants |  |  | 1306 | 1596 | 532 | 759 | 1471 | 960 | 1727 | 799 | 111 | 258 | 20 | 146 | 72 | 53 | 17 | 158 | 9827
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (2142+22)/3457*100=62.3% WHICH IS FURTHER DIVIDED BY 2= 31.2
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (215+1)/217*100=99% Reply: (196+3)/2